## Slide 1: Quark: A Dynamic SDLC Methodology
Vasu Vuppala, Ph.D., PMP
John Vincent, Ph.D.
{vuppala,vincent}@nscl.msu.edu
National Superconducting Cyclotron Laboratory
National Superconducting Cyclotron Laboratory,
East Lansing, Michigan, USA.

## Slide 2: Overview
Background
  Software Crisis
  SDLC Models
  NSCL EE Department Requirements
The Quark Software Process Model
Implementation
Results
Conclusion
“If you can't describe what you are doing as a process, you don't know what you're doing”

## Slide 3: Software Crisis
Software Crisis
  Software Projects Behind Schedule
  Over Budget
  Low Quality
  Difficult to Maintain
  Inefficient
Software Process Models, SDLC Methodologies
  Waterfall, V-Model, Spiral, RUP, Agile (Scrum, XP, FDD,DSDM etc)
Frameworks
  CMMI, ISO 9000-3, PMBOK
Quality Management Systems
  TQM, Six Sigma, Lean Software Development
“Real programmers can write assembly code in any language. -Larry Wall”

## Slide 4: Software Engineering
Four Decades and Still No Light
Software Development: Art, Science, or Black Magic?
Engineering Discipline Futile for Software Development?
Humanist Management
Multi-disciplinary: Psychology, Sociology, Organizational Theory
Personality Types and Roles
Creativity vs Efficiency
Chaos and Creativity
Predictive vs Adaptive
“We adore chaos because we love to produce order. -M. C. Escher”

## Slide 5: NSCL Requirements
Transparent
Predictive
Un-bureaucratic
Low Overhead
Minimal Customer Interaction
Must Not Stifle Creativity
Single Model
“You can always tell a physicist, but you can't tell him much.”

## Slide 6: SDLC Model Selection
 | Waterfall | RUP | Agile | V-Model
Requirements Volatility | Low | High | High | Low
Requirements Clarity | High | Medium | Low | High
Development | Custom | Custom | Custom/Product | Custom/Product
Customer Availability | Low | High | High | Low
Criticality | Low | High | Medium | Medium
Complexity | Low | High | High | Medium
Size | Low | High | Medium | Medium
Customer Involvement | Low | High | High | Low
“Three virtues of a programmer: laziness, impatience, and hubris. -Larry Wall.”

## Slide 7: Quark Model: Elements
Iterations
  Parameterized: Quark Parameters (QMPs)
Projects
  Qualified: Project Characteristics (PCTs)
Project Management
  Integrated
“All science is either physics or stamp collecting. -Ernest Rutherford.”

## Slide 8: Quark Model: QMPs
Duration
Change Control Specification
Planning Detail
Documentation Detail
Communication
Quality Control
“Remember that there is no code faster than no code.”

## Slide 9: Quark Model: Static PCTs
Safety and Security Requirements
Quality Requirements
Timeline Constraints
Customer Availability
Bespoke or off-the-shelf
Contract Type
Team Location
“Brooks Law: Adding manpower to a late software project makes it later!”

## Slide 10: Quark Model: Dynamic PCTs
Requirements Clarity
Customer Requirements Clarity
Size
Technology Expertise
Complexity
Estimate Confidence Level
“Brooks Law: Adding manpower to a late software project makes it later!”

## Slide 11: Quark Model
“The perfect project plan is possible if one first documents a list of all the unknowns.”

## Slide 12: Development Process
“If at first you don't succeed, call it version 1.0”

## Slide 13: Development Process
Refine Requirements and Architecture
Plan for iteration or release (PFI)
Refine design and test plans
Code, Refactor, Unit Test (CRUT)
Release
Deploy and Test
Review
Perform User Acceptance Test (UAT)
“You cannot teach beginners top-down programming, because they don't know which end is up. -Hoare.”

## Slide 14: PM Processes
“I have always found that plans are useless, but planning is indispensable -Eisenhower.”

## Slide 15: Performance Measurement
Earned Value Management (EVM)
Planned Value (PV): Work Scheduled
Earned Value (EV): Work Completed
Actual Cost (AC): Cost Incurred
Cost Performance Index (CPI) = EV/AC
Schedule Performance Index (SPI) = EV/PV
Performance Measured Periodically (Weekly)
“Wirth's law: Software gets slower faster than hardware gets faster.”

## Slide 16: Documentation
Refined Iteratively
QMPs Dictate the Detail Level
SRS and AD Kept in Sync with CRUT of Last Iteration
Essential Documents
  Requirement Specifications, Architecture Document
  Installation Manual, Release Notes, User Manual
  Project Plan, Project Closure Report
“If the code and the comments disagree, then both are probably wrong.”

## Slide 17: Implemenation: SPI
Policies
Procedures
Guidelines, Checklists, Templates, Standards
Software Process Infrastructure (SPI)
“In theory, there is no difference between theory and practice. But, in practice, there is.”

## Slide 18: Implementation
Quark SPI
  Hosted on the Web
  Policies Based on CMMI-Dev 1.2
  Procedures Based on QM, PMBOK-4
  Templates
LEMA
  Project Plan, SRS, AD, PSR, EVM, PQM, PCR
“Nine people can’t make a baby in a month. - Brooks”

## Slide 19: Implementation: Quark Model
“Simplicity is prerequisite for reliability. -Edsger W.Dijkstra.”

## Slide 20: Preliminary Results
All Projects In EE Department Follow QM
PM Processes Being Utilized By Other Groups
First Software Projects:
  Channel Access Protocol on Rabbit CoreModule
  LINAC Emittance Measurement Application (LEMA)
Currently 5 Software And About 15 Hardware Projects Using QM
“Better train people and risk they leave - than do nothing and risk they stay.”

## Slide 21: Results: LEMA
Under Budget
Slight Schedule Slippage Due to Customer Surveys
Customer Satisfaction Survey: 8.4/9
Chart: 
| Dev | Des | Doc | QA | Overall
Productivity | 17.1223 | 14.9686 | 13.4844 | 12.5594 | 10.4615
Chart: 
| Project Management | Training | Design | Implementation | IT | Documentation
Effort | 0.074725 | 0.092308 | 0.087912 | 0.61099 | 0.057143 | 0.076923
“Measuring programming progress by lines of code is like measuring aircraft building progress by weight.”

## Slide 22: Silver Bullet?
Have We Killed The Beast?
Too Early to Say?
Far From It….
Subjective Measurement Of QMPs And PCTs
EVM May Not Be Suitable For All Types Of Projects
Heavier-weight Model (Due To PM)
“For every complex problem there is an answer that is clear, simple, and wrong.”

## Slide 23: Conclusions
In Less Than a Year We Have Moved From Almost No Processes to Mature Processes
Management vs Development
Quark’s Processes Are Still Being Evaluated
Resource Utilization
Current Work
  Objective Measurement Of PCTs And QMPs
  EVM For QM
  Tailoring Integration
  Requirements Traceability
  Project/Release Performance
“The software isn't finished until the last user is dead.”

## Slide 24: Thank you!
“Software and cathedrals are much the same - first we build them, then we pray.”