## Qmodel
Project Quark Model
Project ID |  |  | Project Description | [17 empty] | Work Order
LEMA |  |  | LINAC Emitttance Measurement Application | [17 empty] | 2961-004-EE-002
[18 empty] | Change Control |  | Communication |  | Quality
# | RID | Date | RC | CRC | Size | ECL | TE | CPX | CRT | SSR | QR | TC | CA | CPI | SPI | Duration | Effort | Major | Minor | Team | Customer | Reviews | Tests | DOC | PD
1 | 1.0Alpha | 2010-06-11 | 6 | 6 | 4 | 7 | 4 | 5 | 7 | 3 | 7 | 7 | 7 | 1 | 1 | 3W |  | 2W | 1W | D,10m | W,30m | DR |  | 4 | 4
2 | 1.0Beta | 2010-07-07 | 8 | 7 | 4 | 8 | 7 | 4 | 7 | 3 | 7 | 6 | 7 | 0.97 | 1.11 | 4W |  | 1W | 3D | D,10m | W,30m | CR |  | 7 | 6
3 | 1.0 | 8/2/2010 | 7 | 6 | 6 | 8 | 8 | 4 | 7 | 3 | 7 | 5 | 7 | 0.9 | 1.04 | 3W |  | 3D | 1D | D,10m | W,30m | CF |  | 9 | 7
4 | 2.0Beta | 2010-09-02 | 8 | 8 | 6 | 8 | 8 | 4 | 7 | 3 | 8 | 5 | 5 | 1 | 0.94 | 10W |  | 3D | 1D | W,10m | 2W,30m | DR,CR |  | 7 | 8
5 | 2.0
Note on C8: Release ID
Note on E8: Requirements Clarity
Note on F8: Customer Requirements Clarity
Note on H8: Estimate Confidence Level
Note on I8: Technology Expertise
Note on J8: Complexity
Note on K8: Criticality
Note on L8: Safety & Security Requirements
Note on M8: Quality Requirements
Note on N8: Timeline Constraint
Note on O8: Customer Availablity
Note on R8: W - Weeks M - Months
Note on T8: W- Person Week D - Person Day
Note on U8: W- Person Week D - Person Day
Note on V8: D= Daily W - Weekly BW - Bi-weekly
Note on W8: D= Daily W - Weekly BW - Bi-weekly
Note on X8: DR - Design Review CR - Code Review CSS - Customer Satisfaction Survey
Note on Z8: Documentation Detail
Note on AA8: Planning Detail