## Definitions
Project Performance Metric Definitions
S# | Metric | Abbrev. | Description | Formula/Value
1 | Budget at Completion | BAC | Baseline project cost
2 | Actual Cost | AC | Total costs incurred in completing work during a given period
3 | Earned Value | EV | Physical work completed during a given period
4 | Planned Value | PV | Physical work scheduled for completion during a given period
5 | Cost Variance | CV | Cost overrun during a given period | EV-AC
6 | Cost Performance Index | CPI | Cost efficiency ratio | EV/AC
7 | Schedule Variance | SV | Schedule slipped during a given period | EV-PV
8 | Schedule Performance Index | SPI | Schedule efficiency ratio | EV/PV
9 | Estimate to Completion | ETC | Expected additional cost needed | EAC-AC
10 | Estimate at Completion | EAC | Expected total cost | BAC/CPI
11 | Variance at Completion | VAC | Estimated cost overrun at end of project | BAC-EAC
12 | To-Complete Performance Index | TCPI | Ratio of remaining work and remaining resources
| TCPI Cost | TCPI-C | Ratio of remaining work and remaining funds | BAC-EV)/(BAC-AC)
| TCPI Schedule* | TCPI-S | Ratio of remaing work and remaining time | (BAC-EV)/(BAC-PV)
13 | Status | n/a | Average of CPI and SPI | (CPI+SPI)/2
Status color key:
|  |  | GREEN = On track | ³1.0
|  |  | YELLOW = Slightly behind schedule/budget | ³0.85 but <1.0
|  |  | RED = Needs immediate attention | ³0.65 but <0.85
|  |  | BLACK = Needs to be killed or restored | <0.65
*Note: TCPI-S is not a standard and is not defined in literature.

## Data
Project Performance Report
Project: Formal Software Engineering Processes
Project Manager: Vasu V
|  |  | Budget |  | Earned | Actual | Cost Variance |  | Schedule Variance |  | Performance |  | Forecast |  |  |  | TCPI
ID | Project Name | Date | BAC | PV | EV | AC | $ | % | $ | % | CPI | SPI | ETC | EAC | VAC (%) | VAC ($) | Cost | Sched | Average Index | Status
FSEP | Formal SE Processes | 2009-09-04 | 55350 | 4384 | 7195 | 6250 | 945 | 21.56% | 2811 | 64.12% | 1.1512 | 1.6412 | 41830.2641 | 48080.2641 | 13.13% | 7269.7359 | 0.98075 | 0.94485 | 1.3962 | Green
FSEP | Formal SE Processes | 2009-09-11 | 55350 | 6889.3918 | 8302.5 | 8100 | 202.5 | 2.939% | 1413.1082 | 20.51% | 1.025 | 1.2051 | 45900 | 54000 | 2.439% | 1350 | 0.99571 | 0.97084 | 1.1151 | Green
FSEP | Formal SE Processes | 2009-09-18 | 55350 | 8142.0085 | 9963 | 9325 | 638 | 7.836% | 1820.9915 | 22.37% | 1.0684 | 1.2237 | 42480.5556 | 51805.5556 | 6.404% | 3544.4444 | 0.98614 | 0.96143 | 1.146 | Green
FSEP | Formal SE Processes | 2009-09-25 | 55350 | 9707.7793 | 12730.5 | 10325 | 2405.5 | 24.78% | 3022.7207 | 31.14% | 1.233 | 1.3114 | 34566.3043 | 44891.3043 | 18.9% | 10458.6957 | 0.94657 | 0.93377 | 1.2722 | Green
FSEP | Formal SE Processes | 2009-10-02 | 55350 | 11273.5502 | 14391 | 11425 | 2966 | 26.31% | 3117.4498 | 27.65% | 1.2596 | 1.2765 | 32517.3077 | 43942.3077 | 20.61% | 11407.6923 | 0.93248 | 0.92927 | 1.2681 | Green
FSEP | Formal SE Processes | 2009-10-09 | 55350 | 12839.3211 | 16605 | 12525 | 4080 | 31.78% | 3765.6789 | 29.33% | 1.3257 | 1.2933 | 29225 | 41750 | 24.57% | 13600 | 0.90473 | 0.91142 | 1.3095 | Green
FSEP | Formal SE Processes | 2009-10-16 | 55350 | 14405.0919 | 19372.5 | 13475 | 5897.5 | 40.94% | 4967.4081 | 34.48% | 1.4377 | 1.3448 | 25025 | 38500 | 30.44% | 16850 | 0.85916 | 0.87868 | 1.3912 | Green
FSEP | Formal SE Processes | 2009-10-23 | 55350 | 15970.8628 | 22140 | 14725 | 7415 | 46.43% | 6169.1372 | 38.63% | 1.5036 | 1.3863 | 22087.5 | 36812.5 | 33.49% | 18537.5 | 0.81748 | 0.84334 | 1.4449 | Green
FSEP | Formal SE Processes | 2009-10-30 | 55350 | 17536.6337 | 24354 | 15425 | 8929 | 50.92% | 6817.3663 | 38.87% | 1.5789 | 1.3887 | 19631.8182 | 35056.8182 | 36.66% | 20293.1818 | 0.77636 | 0.81971 | 1.4838 | Green
FSEP | Formal SE Processes | 2009-11-06 | 55350 | 19102.4045 | 26014.5 | 16125 | 9889.5 | 51.77% | 6912.0955 | 36.18% | 1.6133 | 1.3618 | 18183.5106 | 34308.5106 | 38.02% | 21041.4894 | 0.74788 | 0.80931 | 1.4876 | Green
FSEP | Formal SE Processes | 2009-11-13 | 55350 | 20668.1754 | 26568 | 17475 | 9093 | 44% | 5899.8246 | 28.55% | 1.5203 | 1.2855 | 18931.25 | 36406.25 | 34.23% | 18943.75 | 0.75992 | 0.82989 | 1.4029 | Green
FSEP | Formal SE Processes | 2009-11-20 | 55350 | 22233.9463 | 27675 | 18000 | 9675 | 43.51% | 5441.0537 | 24.47% | 1.5375 | 1.2447 | 18000 | 36000 | 34.96% | 19350 | 0.74096 | 0.8357 | 1.3911 | Green
FSEP | Formal SE Processes | 2009-11-27 | 55350 | 23799.7171 | 28782 | 18950 | 9832 | 41.31% | 4982.2829 | 20.93% | 1.5188 | 1.2093 | 17492.3077 | 36442.3077 | 34.16% | 18907.6923 | 0.72989 | 0.84208 | 1.3641 | Green
FSEP | Formal SE Processes | 2009-12-04 | 55350 | 25365.488 | 30442.5 | 19975 | 10467.5 | 41.27% | 5077.012 | 20.02% | 1.524 | 1.2002 | 16343.1818 | 36318.1818 | 34.38% | 19031.8182 | 0.7041 | 0.83068 | 1.3621 | Green
FSEP | Formal SE Processes | 2009-12-11 | 55350 | 26931.2588 | 31549.5 | 20425 | 11124.5 | 41.31% | 4618.2412 | 17.15% | 1.5447 | 1.1715 | 15408.3333 | 35833.3333 | 35.26% | 19516.6667 | 0.68147 | 0.83749 | 1.3581 | Green
FSEP | Formal SE Processes | 2009-12-18 | 55350 | 28497.0297 | 33210 | 21875 | 11335 | 39.78% | 4712.9703 | 16.54% | 1.5182 | 1.1654 | 14583.3333 | 36458.3333 | 34.13% | 18891.6667 | 0.66139 | 0.82449 | 1.3418 | Green
FSEP | Formal SE Processes | 2010-01-08 | 55350 | 31628.5714 | 35424 | 23375 | 12049 | 38.1% | 3795.4286 | 12% | 1.5155 | 1.12 | 13148.4375 | 36523.4375 | 34.01% | 18826.5625 | 0.62317 | 0.84 | 1.3177 | Green